## Summary
InsightHub BRD — QA Status Report
Sprint: USA Launch · Audit Date: 2026-07-18 · Total Stories: 69
Total Stories | PASS / Built | PARTIAL | GAP / Not Built
69 | 36 | 8 | 25
Overall Completion (PASS): 52% ¦ USA Sprint Target: Phase 0 + Phase 1 + Phase 2
Phase | Total | PASS | PARTIAL | GAP
Phase 0 | 14 | 14 | 0 | 0
Phase 1 | 21 | 16 | 2 | 3
Phase 2 | 14 | 6 | 4 | 4
Phase 3 | 13 | 0 | 2 | 11
Phase 4 | 7 | 0 | 0 | 7
Legend
PASS | Fully implemented and verified in code audit
PARTIAL | Code exists but incomplete, not wired, or needs further work
GAP | Not built — required for USA launch sprint

## Phase_0
Phase_0
Story ID | User Story | Role / User | Test Scenario | Expected Result | Status | QA Notes / Evidence
US-101 | Admin login with role enforcement | admin | A global admin logs in at /login and lands on admin dashboard | Login works, role = admin | PASS | All roles verified. Admin sees full tenant list.
US-102 | Tenant admin login | tenant_admin | Tenant admin logs in and sees only their tenant's data | Tenant isolation confirmed | PASS | Tenant 'Gratiture Solutions' data fully isolated.
US-103 | Viewer login (read-only) | viewer | Viewer can see all tabs but cannot upload or manage users | Upload tab hidden for viewer | PASS | is_viewer flag blocks upload & admin controls.
US-104 | CA / Accountant role login | ca | CA role can view billing, GST tabs; cannot upload | CA tab access confirmed | PASS | is_ca flag enforced in render_tab.
US-105 | Multi-tenant data isolation | tenant_admin | Each tenant sees only their own uploaded data | Cross-tenant query returns nothing | PASS | tenant_id filter on all DB queries.
US-106 | Tenant onboarding flow | admin | Admin creates new tenant via Onboarding tab | Tenant row created in DB | PASS | onboarding.py creates tenant + default users.
US-107 | File upload — Sales CSV | tenant_user | User uploads a sales CSV via Upload tab | Rows appended to sales DB table | PASS | parse_upload + append_upload_to_db confirmed.
US-108 | File upload — Purchase CSV | tenant_user | User uploads a purchase CSV | Rows appended to purchases table | PASS | Both sales & purchase upload paths work.
US-109 | KPI cards render on Overview | viewer | Overview tab shows Sales, Purchases, Margin, Bills cards | 4 KPI cards visible with correct values | PASS | kpi_card() renders all 4 metrics.
US-110 | Charts render without overflow | viewer | Revenue & Customer tab charts do not overlap below content | Charts contained in fixed-height containers | PASS | Fixed: style={'height':'280px'} on all dcc.Graph.
US-111 | PDF export download | tenant_user | User clicks Download PDF, file downloads | File: insighthub_report_YYYYMMDD.pdf | PASS | pdf_report.py generates PDF. No MedStar refs.
US-112 | CSV export — Sales | tenant_user | User downloads sales data as CSV | File: sales_export.csv | PASS | download callback returns dcc.send_data_frame.
US-113 | CSV export — Purchases | tenant_user | User downloads purchases data as CSV | File: purchases_export.csv | PASS | No MedStar branding in filename or headers.
US-114 | Branding — zero MedStar references | any | No 'MedStar Pharmacy' visible anywhere in product | Zero pharmacy/MedStar strings in UI | PASS | Scrubbed from filenames, PDF header, placeholders, docstrings.

## Phase_1
Phase_1
Story ID | User Story | Role / User | Test Scenario | Expected Result | Status | QA Notes / Evidence
US-201 | Multi-tenant DB isolation | tenant_admin | All queries scoped by tenant_id | No cross-tenant data leak | PASS | tenant_id column on all tables; filter on load.
US-202 | Tenant admin: create users | tenant_admin | Tenant admin creates viewer/ca user within their tenant | New user appears in user list | PASS | Admin tab > Users panel supports add/deactivate.
US-203 | Role-based tab visibility | all | Admin sees all tabs; viewer/ca see restricted set | Tabs render per role correctly | PASS | Tab list built dynamically from is_admin/is_ca/is_viewer flags.
US-204 | Cash / credit payment split | tenant_user | Overview or Sales tab shows cash vs. credit breakdown | Pie or bar chart showing payment types | PASS | Cashflow tab exists with payment type chart.
US-205 | SMS alerts — Twilio | tenant_admin | Configure phone, trigger margin alert → SMS sent | Twilio API called with correct body | PARTIAL | alerts.py has full Twilio code (TWILIO_SID, send_alert) but not wired to per-tenant scheduled jobs. Wire via scheduler.py to complete.
US-206 | WhatsApp alerts — Interakt/WATI | tenant_admin | Configure WhatsApp, trigger alert → WA message sent | Interakt/WATI API called | PARTIAL | _send_whatsapp_interakt() and _send_whatsapp_wati() implemented. Not wired to tenant settings UI scheduler.
US-207 | Weekly email digest | tenant_admin | Every Monday 8am EST, email digest sent to tenant | Email received with KPI summary | PASS | email_reports.py + APScheduler wired in app.py startup.
US-208 | Expiry / stock alerts | tenant_admin | Items expiring <30 days trigger alert | Alert sent via configured channel | PASS | expiry_dashboard.py + alerts.py send_expiry_alert.
US-209 | Stock below threshold alert | tenant_admin | Item quantity drops below threshold → alert | Alert includes item name, qty, branch | PASS | send_stock_alert() in alerts.py implemented.
US-210 | PDF report generation | tenant_user | Download PDF with charts & KPI summary | Professional PDF, no legacy branding | PASS | pdf_report.py uses ReportLab. Header: InsightHub Analytics Report.
US-211 | Marg ERP / GoFrugal import | tenant_user | Upload Marg ERP XML/CSV → auto-detected & parsed | Marg-format rows appear in DB | GAP | No Marg ERP parser exists. BRD requires native Marg XML format support. Needs: integrations/marg_erp.py.
US-212 | Branch compare tab | tenant_user | Compare tab shows side-by-side branch performance | Bar/scatter chart per branch | PASS | compare tab in tenant_analytics.py with multi-branch selector.
US-213 | CA role: billing tabs only | ca | CA user can access GST/billing tabs but not admin/upload | Upload tab hidden; billing tab visible | PASS | is_ca enforced in render_tab; upload_card hidden.
US-214 | 7 domain verticals | admin | Domain config supports pharmacy/saas/retail/accounting/restaurant/healthcare/generic | All 7 domains in DOMAIN_CONFIGS | PASS | domain_config.py now has 7 domains (restaurant + healthcare added this sprint).
US-215 | YoY year selector | tenant_user | Year-over-Year tab has dropdown to select comparison year | Changing year rerenders charts | PASS | yoy-year-select dcc.Dropdown + callback in yoy_report.py.
US-216 | GoFrugal API import | tenant_user | Connect GoFrugal API, auto-pull data on schedule | GoFrugal rows synced to DB | GAP | No GoFrugal connector built. Needs integrations/gofrugal.py with API auth.
US-217 | Password reset via email OTP | any | User requests reset → email with 6-digit code → new password set | Password updated; old password fails login | PASS | password_reset.py built this sprint: /forgot-password + /reset-password routes with SendGrid OTP.
US-218 | Stripe billing: $39/$99 plans | tenant_admin | Tenant subscribes via Stripe checkout, plan stored in DB | Subscription active, feature gates apply | PASS | stripe_billing.py + billing.py with PLANS={starter:39, growth:99}.
US-219 | TOTP / MFA | any | User enables MFA via /mfa/setup, subsequent logins require 6-digit TOTP | Login flow enforces TOTP after password | PASS | mfa.py fully built: setup/verify/disable routes, QR code, pyotp.
US-220 | 14-day free trial | new user | Signup creates subscription with 14-day trial, no card required | trial_end set 14 days from signup; dashboard accessible | PASS | signup.py passes trial_period_days=14 to Stripe.
US-221 | i18n — multi-language UI | tenant | UI rendered in English, Hindi, or tenant locale | Selected language renders all labels translated | GAP | No i18n module or translation files exist. Needs: i18n.py, locale JSONs (en, hi, es).

## Phase_2
Phase_2
Story ID | User Story | Role / User | Test Scenario | Expected Result | Status | QA Notes / Evidence
US-301 | Square POS import | tenant_user | Upload Square POS CSV → auto-detected and parsed | Square columns mapped to sales schema | GAP | No Square parser. FORMAT_TO_DOMAIN maps 'square' → retail but no parser. Needs: integrations/square.py.
US-302 | QuickBooks import | tenant_user | Connect QuickBooks OAuth → pull P&L into dashboard | QuickBooks data synced | PARTIAL | integrations/quickbooks.py exists with OAuth skeleton + init_qb_tables / register_qb_routes. Data pull not implemented.
US-303 | Shopify import | tenant_user | Upload Shopify orders export → parsed as retail sales | Shopify columns mapped | GAP | No Shopify parser. FORMAT_TO_DOMAIN maps 'shopify' → retail but no file. Needs: integrations/shopify.py.
US-304 | Anomaly detection | tenant_user | AI flags unusual spikes or drops in revenue/costs | Anomaly markers on chart, alert fired | GAP | No anomaly detection module. ai/rag.py exists but no statistical anomaly detection. Needs: ai/anomaly.py.
US-305 | USA sales tax summary | tenant_user | Tax summary tab shows state-wise sales tax breakdown | State → tax amount table visible | PARTIAL | gst_report.py has state_grp groupby for US state tax. UI label still shows GST (India). Needs: rename & separate US Sales Tax tab.
US-306 | CCPA compliance | any | Privacy policy, data deletion request, consent toggle | Delete-my-data endpoint, cookie consent | GAP | No CCPA module. No /privacy, /data-deletion routes, no consent banner.
US-307 | Auto narrative after upload | tenant_user | After upload, AI generates plain-English summary of loaded data | Summary card appears below upload confirmation | PASS | _generate_upload_narrative() built this sprint: shows row count, total sales, avg margin, top item after upload.
US-308 | AI Chat / RAG insights | tenant_user | AI Insights tab lets user ask questions in natural language | Answer returned using uploaded data context | PASS | ai/rag.py + ai/groq_client.py. render_ai_chat_tab() in app.py. Groq LLM for answers.
US-309 | Referral program | tenant | Tenant shares referral link; new signup credits referrer | Referral tracked, discount applied | PASS | referral.py with init_referral_tables + register_referral_routes.
US-310 | Multi-currency display | tenant | Dashboard switches between ₹ INR and $ USD | All KPIs, charts, tables use selected currency symbol | PASS | _fmt(v, currency) used throughout. Currency selector in sidebar.
US-311 | Domain-adaptive UI | tenant | After upload, UI relabels tabs/KPIs for detected domain | Pharmacy → 'Bills'; Retail → 'Orders' | PASS | domain_config.py + get_domain_config() drives all labels. 7 domains supported.
US-312 | Marketing landing page | public | / or /landing shows professional SaaS landing page | Hero, features, pricing, testimonials visible | PASS | landing_page.py with full HTML: hero, features grid, 3-tier pricing, testimonials, CTA.
US-313 | White-label tenant portal | admin | Admin can set tenant logo, color, name via portal | Tenant dashboard shows their branding | PARTIAL | onboarding.py + tenant_name shown in navbar. No custom logo/color upload UI yet.
US-314 | Advanced permission matrix | admin | Granular permissions per role per module (read/write/admin) | Role-module matrix configurable in admin UI | PARTIAL | Role system (admin/tenant_admin/viewer/ca/tenant_user) is solid. No UI matrix for custom per-module permissions.

## Phase_3
Phase_3
Story ID | User Story | Role / User | Test Scenario | Expected Result | Status | QA Notes / Evidence
US-401 | API rate limiting | admin | API endpoints rate-limited per tenant (e.g. 100 req/min) | 429 returned when limit exceeded | GAP | No rate limiting middleware. Flask-Limiter not installed.
US-402 | Audit log | admin | All user actions (login, upload, export) logged with timestamp | Audit log table populated and viewable | GAP | No audit_log table or logging middleware.
US-403 | Data retention policy | admin | Old upload data purged after configurable retention period | Rows older than N days deleted on schedule | GAP | No retention policy. Data accumulates indefinitely.
US-404 | Bulk user import | tenant_admin | Admin uploads CSV of users → all created in one action | Users created, welcome emails sent | GAP | Only single-user creation via UI form.
US-405 | Custom report builder | tenant | User drags and drops KPIs/charts to build custom report | Custom report saved and re-openable | GAP | No report builder. Only fixed tabs.
US-406 | Scheduled reports | tenant_admin | Configure report to email every Mon/Thu at 8am | Email sent on schedule with PDF attached | PARTIAL | email_reports.py sends weekly digest. No per-tenant custom schedule UI.
US-407 | SSO / OAuth login | any | Login with Google or Microsoft SSO | OAuth flow completes, user created/found | GAP | No SSO. Only username/password + TOTP MFA.
US-408 | Data backup / export all | admin | Admin exports all tenant data as ZIP (CSVs) | ZIP file with sales.csv, purchases.csv per tenant | GAP | No bulk export endpoint.
US-409 | Webhook notifications | tenant_admin | Configure webhook URL; events POSTed on upload/alert | POST received at configured URL | GAP | No webhook system.
US-410 | Custom domain (CNAME) | tenant | Tenant maps analytics.mycompany.com to InsightHub | Custom domain resolves to tenant dashboard | GAP | No custom domain / CNAME support.
US-411 | Team collaboration — comments | tenant | Users can comment on a specific chart or KPI | Comment visible to all team members | GAP | No commenting system.
US-412 | Mobile responsive dashboard | any | Dashboard usable on mobile (375px+) | Charts and KPIs stack vertically on mobile | PARTIAL | Bootstrap grid used. dcc.Graph responsive=True. Not fully optimized for 375px.
US-413 | Dark mode | any | User toggles dark mode; all charts update colors | Dark background, light text throughout | GAP | No dark mode toggle or theming system.

## Phase_4
Phase_4
Story ID | User Story | Role / User | Test Scenario | Expected Result | Status | QA Notes / Evidence
US-501 | Enterprise SSO (SAML) | enterprise | SAML-based SSO with IdP like Okta/Azure AD | SAML assertion validates, user session created | GAP | No SAML module.
US-502 | Dedicated tenant DB (schema isolation) | enterprise | Each enterprise tenant on separate DB schema | DB-level isolation, not row-level | GAP | SQLite row-level isolation only. No per-tenant schema.
US-503 | SLA & uptime dashboard | admin | Admin sees real-time uptime, p95 latency per tenant | Uptime > 99.9% tracked and displayed | GAP | No monitoring dashboard integrated.
US-504 | Kubernetes / auto-scaling | devops | App scales horizontally on traffic spike | Pod count increases, load distributed | GAP | Single-process Dash app. No K8s config.
US-505 | SOC 2 Type II readiness | compliance | Controls in place for CC6.1, CC7.2, CC9.2 etc. | Evidence package generated | GAP | No compliance controls or evidence collection.
US-506 | ERP connectors (SAP, Oracle) | enterprise | Native SAP/Oracle data sync via API | ERP rows appear in dashboard automatically | GAP | No ERP connectors.
US-507 | Custom AI model fine-tuning | enterprise | Tenant uploads labeled Q&A pairs; AI fine-tuned on their data | AI answers reflect tenant-specific knowledge | GAP | Base Groq/LLaMA RAG only. No fine-tuning pipeline.

## USA_Sprint_Actions
InsightHub — USA Sprint Action Plan (Gaps Only)
Story | Description | What to Build | Priority | Effort | Status
US-205 | SMS Alerts wiring | Wire alerts.py Twilio send_alert() to per-tenant scheduled job trigger in scheduler.py | P1 – HIGH | S (1 day) | TODO
US-206 | WhatsApp Alerts wiring | Wire _send_whatsapp_interakt/wati() to tenant settings + scheduler | P1 – HIGH | S (1 day) | TODO
US-211 | Marg ERP Import | Build integrations/marg_erp.py: parse Marg XML/CSV → sales/purchase schema | P2 – MED | M (3 days) | TODO
US-216 | GoFrugal API Connector | Build integrations/gofrugal.py: OAuth + REST API data pull → DB sync | P2 – MED | M (3 days) | TODO
US-221 | i18n — Multi-language | Build i18n.py with locale JSONs (en, hi, es); language selector in sidebar | P2 – MED | L (5 days) | TODO
US-301 | Square POS Import | Build integrations/square.py: parse Square CSV export → retail sales schema | P1 – HIGH | S (2 days) | TODO
US-302 | QuickBooks Data Pull | Complete integrations/quickbooks.py: implement data-pull after OAuth completes | P1 – HIGH | M (3 days) | IN PROGRESS
US-303 | Shopify Import | Build integrations/shopify.py: parse Shopify orders CSV → retail sales schema | P1 – HIGH | S (2 days) | TODO
US-304 | Anomaly Detection | Build ai/anomaly.py: Z-score or IQR detection on revenue/cost time series | P2 – MED | M (3 days) | TODO
US-305 | USA Sales Tax Tab | Rename GST tab to 'Sales Tax' for US tenants; split state tax view from GST view | P1 – HIGH | S (1 day) | TODO
US-306 | CCPA Compliance | Add /privacy route, /data-deletion endpoint, cookie consent banner | P1 – HIGH | M (3 days) | TODO
US-313 | White-label branding | Add logo upload + primary color picker to onboarding/tenant settings | P2 – MED | M (3 days) | TODO
US-401 | API Rate Limiting | Install flask-limiter; @limiter.limit('100/minute') on API endpoints | P2 – MED | S (0.5 days) | TODO
US-402 | Audit Log | Create audit_log table; log login/upload/export/role-change events | P2 – MED | S (1 day) | TODO
US-407 | Google/Microsoft SSO | Add flask-dance OAuth blueprint for Google + Microsoft login | P3 – LOW | L (5 days) | TODO